Project Brief: "Project X" Go-to-Market Campaign

Project: Project X Launch Date: Jan 15, 2024 Owner: Marketing Lead

1. Project Summary

Project X is our new flagship SaaS platform for automated operations management. This document outlines the marketing campaign brief for its official public launch on March 1, 2024. This is an internal document for planning.

2. The Goal

To generate 5,000 new trial sign-ups and $150,000 in attributed pipeline revenue within the first 60 days of launch (by May 1, 2024).

3. Target Audience

- Primary Persona: "Operations Olivia" - VP of Operations, 40-55, overwhelmed by manual reporting, looking for a single source of truth, measures success by team efficiency and cost reduction.

- Secondary Persona: "IT Ivan" - IT Director, 35-50, concerned with security, integration, and scalability. Needs to approve the technical fit.

4. Key Messaging

- Core Message: "Stop Chasing Data. Start Making Decisions."

- Pillar 1 (for Olivia): "Automate 80% of your manual reporting and reclaim your team's time. Get the ROI you've been missing."

- Pillar 2 (for Ivan): "Secure, scalable, and built to integrate. Project X fits your stack, no compromises."

- Keywords: automation, ROI, conversion, integration, scalable, reporting, single source of truth.

5. Deliverables

- Landing Page: High-conversion focused page with demo video and sign-up form.

- Email Launch Sequence: 5-part nurture stream for new leads.

- Ad Creative: Sets for Google, LinkedIn, and Capterra.

- Sales Deck: Updated sales enablement material.

- Press Kit: For PR outreach.

6. Timeline

- Jan 22: Campaign kickoff

- Feb 15: All assets complete and approved

- Feb 20-28: "Hype" phase (teasers on social)

- March 1: LAUNCH DAY

- March 1 - May 1: "Amplify" phase (ad spend, webinars, PR)