Official Report: Q3 2024 Marketing Campaign Analysis

Date: October 15, 2024 Author: Marketing Department

1. Executive Summary

The Q3 2024 period saw a focused effort on two primary initiatives: the "Summer Surge" campaign (part of Project Y) and the initial launch of the "Project X" platform beta. Overall engagement increased by 22% quarter-over-quarter, driven primarily by strong video performance. However, conversion rates from these campaigns were 5% below target, indicating a need to optimize our funnel.

Return on Investment (ROI) for Q3 was calculated at 2.5:1, a slight decrease from Q2 (2.8:1), attributed to higher ad spend on the new Project X launch.

2. "Summer Surge" Campaign (Project Y)

Objective: Increase brand awareness and top-of-funnel leads.

- Channels: Instagram (Reels), TikTok, YouTube (Shorts)

- Impressions: 4.5 Million

- Engagement: 310,000 (likes, shares, comments)

- Leads Generated: 4,200

- Summary: The campaign successfully met its engagement goals. The video content resonated well, but lead quality was mixed. We recommend re-evaluating our lead-capture form to better qualify prospects in Q4.

3. "Project X" Beta Launch

Objective: Drive initial sign-ups and gather user feedback for the new platform.

- Channels: LinkedIn, Targeted Email, Google Ads

- Sign-ups: 1,850 (Target: 2,000)

- Cost Per Acquisition (CPA): $45 (Target: $40)

- Summary: The launch was moderately successful. While sign-ups were just shy of the goal, the feedback collected has been invaluable. The higher CPA is noted and will be addressed by refining ad creative and audience targeting.

4. Key Learnings & Q4 Recommendations

- Video is Key: Our audience is highly receptive to short-form video. Double down on this for the Q4 holiday campaign.

- Funnel Optimization: The drop in conversion rates highlights a gap between engagement and action. A/B testing landing pages for Project X is a top priority.

- Budget Allocation: Shift 10% of the Q4 budget from generic display ads to targeted LinkedIn content for Project X to improve lead quality and lower CPA.