Project Brief: "Project Y" Q3 2024 Refresh Campaign

Project: Project Y Refresh Date: June 5, 2024 Owner: Marketing Lead

1. Project Summary

Project Y is our established analytics tool, which has a solid, long-term user base. However, new user acquisition has flattened, and engagement from existing users on newer features is low. This campaign ("Summer Surge") aims to re-engage existing users and attract new sign-ups by highlighting key differentiators and newly-released features.

2. The Goal

- Increase engagement (measured by Daily Active Users) from the existing user base by 25%.

- Drive 4,000 new, high-quality MQLs (Marketing Qualified Leads) for the Project Y funnel.

- Promote adoption of the new "Automated Insights" and "Cross-Channel" features.

3. Target Audience

- Primary (New Users): Marketing Managers at small-to-midsize businesses (SMBs) who are currently using basic analytics (like Google Analytics) but feel overwhelmed and need clearer, actionable insights.

- Secondary (Existing Users): Current Project Y users who have been on the "Basic" plan for 6+ months or who are not actively using features launched in the last year.

4. Key Messaging

- Core Message: "Stop Guessing. Start Seeing."

- Pillar 1 (New Users): "Go beyond pageviews. Project Y delivers the 'why' behind your data. Get actionable insights in minutes, not hours."

- Pillar 2 (Existing Users): "You've seen the 'what'—now get the 'why.' Unlock the full power of your Project Y account with Automated Insights."

- Keywords: analytics, marketing reports, data visualization, engagement, leads, ROI, insights.

5. Deliverables

- Landing Page (New Users): A/B test of "features" vs. "benefits" landing page.

- In-App Pop-ups (Existing Users): Banners highlighting the new features.

- Email Sequence: A 3-part "re-engagement" series for dormant users.

- Social Media (Video): A heavy push on short-form video (Reels/Shorts) showing quick, impressive "wins" using Project Y. This will be the core of the "Summer Surge" campaign.

- Updated Help Docs: Clear, simple guides for the new features.

6. Timeline

- June 15: Campaign kickoff & creative brief.

- June 30: All assets complete and approved.

- July 5: "Summer Surge" Campaign Launch.

- July 5 - Aug 30: "Amplify" phase (social ad spend, email sends).

- Sept 1: Begin reporting and analysis (to feed into the Q3 Campaign Report).